**STANTON LACY PARISH QUEENS JUBILEE CELEBRATIONS**

**List of activities as of 24th March 2022 – subject to amendment**

|  |  |  |  |
| --- | --- | --- | --- |
| **WHAT** | **WHERE** | **LEAD** | **TIME** |
| Jubilee avenue of trees in California woods | Hall | AJG | March/April |
| Planting of Jubilee trees | Church/Hall | JA/ST/MJ | 26th March/April |
| Pudding competition | Hall |  | 28th May (Comm Mkt) 10am-1pm |
| Exhibition – old photographs, paintings, stamps | Church | JA/ST | 2nd-5th June + |
| Floral displays in red, white and blue | Church & Hall | ST/MJ | 2nd – 5th June |
| The Queen and stamps - talk | Hall | MJ | 2nd June 7pm |
| ‘Street Party’ | Hall  | All | 3rd June 2pm-late |
| Bonfire/Beacon | TBA | AJG | TBA |
| Church Bell-ringing | Church | JA | 4th June 2.30pm |
| Disco and live band | Hall | AJG/MJ | 4th June 7pm-late |
| Organ recital | Church | JA | 5th June c.2.30pm |
| Green canopy – commemorative tree dedication | Church | JA | 5th June 9.15am |
| Ludlow Male Voice Choir – Jubilee concert | Church | JA | 24th June |

SPECIFIC ACTIONS FROM STEERING GROUP MEETING 24th MARCH:

Ascertain Downton Hall willingness to support an avenue of trees in California woods Alan

Check with Anita as to whether Anita/Fergus could do a BBQ on the 4th June Mervyn/Jo

Check contribution of SL Art Group in exhibition Mervyn

Confirm possibility of beacon or bonfire nearby to Village Hall Alan/Robin

Confirm TV coverage for potential screening in hall Mervyn

Check availability of ball play area Mervyn

Get input into Ripples/West of Clee into Sarah by 18th April All